## Gantchart
PROJECT TITLE |  | DefenseLedger – Blockchain-Powered Ammunition and Supply Chain |  |  |  |  | INSTUTUTE & DEPARTMENT NAME |  | A.P SHAH INSTITUTE OF TECHNOLOGY -CSE(DS)
PROJECT GUIDE |  | Prof. Sarala Mary and Prof. Richa Singh |  |  |  |  | DATE |  | 2025-02-04
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE |  |  |  | PHASE TWO |  |  | PHASE THREE |  |  | PHASE FOUR
[7 empty] | WEEK 1 | WEEK 2 |  | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12
1 | Project Conception and Initiation
1.1 | Research paper search | Tanaya Patil, Ayush Mistry | 2024-02-08 | 8-16-24 | 2 | 100%
1.1.1 | Research paper finalization | Tanaya Patil, Ayush Mistry | 2024-02-08 | 8-16-24 | 2 | 100%
1.2 | Project Title | Tanaya Patil, Ayush Mistry,Sahil Mujumdar,Mayank Kumar | 2024-02-08 | 8-16-24 | 2 | 100%
1.3 | Abstract | Tanaya Patil, Ayush Mistry,Sahil Mujumdar,Mayank Kumar | 2024-02-08 | 8-16-24 | 2 | 100%
1.4 | Objectives | Tanaya Patil, Ayush Mistry,Sahil Mujumdar,Mayank Kumar | 2024-02-08 | 8-16-24 | 2 | 100%
1.5 | Literature Review | Tanaya Patil, Sahil Mujumdar | 8-30-24 | 2024-06-09 | 2 | 100%
1.6 | Problem Definition | Ayush Mistry, Mayank Kumar | 8-30-24 | 8-23-24 | 2 | 100%
1.7 | Scope | Ayush Mistry, Mayank Kumar | 8-30-24 | 8-23-24 | 2 | 100%
1.8 | Technology stack | Sahil Mujumdar, Mayank Kumar | 8-30-24 | 8-23-24 | 2 | 100%
1.9 | Benefits for environment | Ayush Mistry, Mayank Kumar | 8-30-24 | 8-23-24 | 2 | 100%
1.1 | Benefits for society | Ayush Mistry, Mayank Kumar | 8-30-24 | 8-23-24 | 2 | 100%
1.11 | Applications | Tanaya Patil, Sahil Mujumdar | 8-30-24 | 2024-06-09 | 2 | 100%
2 | Project Design
2.1 | Proposed System | Tanaya Patil, Ayush Mistry,Sahil Mujumdar,Mayank Kumar | 8-30-24 | 9-25-24 | 4 | 100%
2.2 | Design(Flow Of Modules) | Tanaya Patil, Ayush Mistry,Sahil Mujumdar,Mayank Kumar | 8-30-24 | 9-25-24 | 4 | 100%
2.3 | Activity Diagram | Tanaya Patil, Sahil Mujumdar | 8-30-24 | 9-25-24 | 4 | 100%
2.4 | Use Case Diagram | Tanaya Patil, Sahil Mujumdar | 8-30-24 | 9-25-24 | 4 | 100%
2.5 | Sequence Diagram | Tanaya Patil, Sahil Mujumdar | 8-30-24 | 9-25-24 | 4 | 100%
2.6 | Description Of Use Case | Tanaya Patil, Sahil Mujumdar | 8-30-24 | 9-25-24 | 4 | 100%
2.7 | Modules | Tanaya Patil, Ayush Mistry,Sahil Mujumdar,Mayank Kumar | 8-30-24 | 9-25-24 | 4 | 100%
2.7.1 | Application Module | Tanaya Patil, Ayush Mistry,Sahil Mujumdar,Mayank Kumar | 8-30-24 | 9-25-24 | 4 | 100%
2.8 | Preparation Of Report | Ayush Mistry, Mayank Kumar | 8-30-24 | 9-25-24 | 4 | 100%
3 | Project Implementation
3.1 | Login,Registration | Ayush Mistry, Mayank Kumar,Sahil Mujumdar | 8-30-24 | 9-25-24 | 4 | 100%
3.2 | Modules Implementation | Tanaya Patil, Ayush Mistry,Sahil Mujumdar,Mayank Kumar | 8-30-24 | 9-25-24 | 4 | 100%
4 | Testing
4.1 | Login Page | Tanaya Patil, Ayush Mistry,Sahil Mujumdar,Mayank Kumar | 8-30-24 | 9-25-24 | 4 | 100%
4.1.1 | Role-Based Access Control (RBAC) with Smart Contracts | Tanaya Patil, Sahil Mujumdar | 8-30-24 | 9-25-24 | 4 | 100%
4.1.2 | Blockchain UI for admin side | Ayush Mistry, Mayank Kumar | 8-30-24 | 9-25-24 | 4 | 100%
4.1.3 | Smart Contract Development Environment Setup | Sahil Mujumdar | 8-30-24 | 9-25-24 | 4 | 100%
4.1.4 | Basic Blockchain Ledger Implementation for Transactions | Tanaya Patil, Sahil Mujumdar | 8-30-24 | 9-25-24 | 4 | 100%
4.1.5 | Smart Contract Implementation for admin side | Tanaya Patil, Sahil Mujumdar | 8-30-24 | 9-25-24 | 4 | 100%
4.1.6 | Integration of Meta Mask with UI (admin side) | Sahil Mujumdar | 8-30-24 | 9-25-24 | 4 | 100%
4.1.7 | Blockchain UI for user side | Tanaya Patil, Ayush Mistry,Sahil Mujumdar,Mayank Kumar | 8-30-24 | 9-25-24 | 4 | 100%
4.1.8 | Smart Contract Implementation for client side | Sahil Mujumdar | 8-30-24 | 9-25-24 | 4 | 100%
4.1.9 | Integration of Meta Mask with UI (client side) | Sahil Mujumdar | 8-30-24 | 9-25-24 | 4 | 100%
4.2 | Testing & Deployment of Blockchain Infrastructure | Tanaya Patil, Sahil Mujumdar | 8-30-24 | 9-25-24 | 4 | 100%
4.2.1 | Data Collection & Preprocessing | Ayush Mistry, Mayank Kumar | 9-25-24 | 2021-07-23 | 4 | 100%
4.2.2 | Home Page UI for Ammunition Supply Chain Dashboard | Ayush Mistry, Mayank Kumar | 9-25-24 | 2025-02-04 | 4 | 100%
4.2.3 | Admin Page UI for Managing Ammunition Data | Ayush Mistry, Mayank Kumar | 9-25-24 | 2025-02-04 | 4 | 100%
4.2.4 | Database Setup for ML Model Training & Predictions | Sahil Mujumdar | 9-25-24 | 2025-02-04 | 4 | 100%
4.2.5 | Development of ML Model | Tanaya Patil | 9-25-24 | 2025-02-04 | 4 | 100%
4.2.6 | Ammunition Supply & Demand Visualization on GUI | Tanaya Patil, Sahil Mujumdar | 9-25-24 | 2025-02-04 | 4 | 100%
4.2.7 | Live Tracking & Prediction of Ammunition Consumption Trends | Tanaya Patil, Sahil Mujumdar | 9-25-24 | 2025-02-04 | 4 | 100%
5 | Report Preparation
5.1 | Black Book | Ayush Mistry, Mayank Kumar | 3-15-2025 | 2025-02-04 | 2 | 100%
5.1 | PPT | Tanaya Patil, Sahil Mujumdar | 3-15-2025 | 2025-02-04 | 2 | 100%
5.1 | Gantt Chart | Tanaya Patil | 3-15-2025 | 2025-02-04 | 2 | 100%